## Ticket Backlog
Fund&Trace — MVP Ticket Backlog
Import into Jira (CSV) or Notion (CSV/table). Columns map to standard Jira fields: Summary, Description, Assignee, Epic, Priority, Points, Labels, Status.
Ticket ID | PI / Iteration | Epic | Title (Summary) | Description | Owner (Assignee) | Priority | Story Points | Dependencies / Blocked by | Acceptance Criteria | Status
FT-001 | PI 0 — Foundation & Setup | Strategy & Scope | Lock launch geography | Confirm UK donors -> Nigeria/Kenya/Ghana as the pilot corridor, based on Stripe+Paystack coverage overlap. | You (Business & Growth) | P0 — Blocker | 2 | None | Written decision doc naming the 3 launch countries and rationale, shared with team. | Not started
FT-002 | PI 0 — Foundation & Setup | Strategy & Scope | Draft platform fee & tip structure | Set initial explicit platform fee % (recommended 3-5%) and tip prompt approach, to give Pricing Analyst a number to build against. | You (Business & Growth) | P0 — Blocker | 2 | None | Fee % and tip UX approach documented and approved by team. | Not started
FT-003 | PI 0 — Foundation & Setup | Infra | Stand up base infrastructure | Create repo, staging/prod environments, and a basic CI/CD skeleton so future work isn't deployed by hand. | DevOps / Cloud / Pricing Analyst | P0 — Blocker | 3 | None | Repo exists; staging + prod environments provisioned; pipeline runs a build on push. | Not started
FT-004 | PI 0 — Foundation & Setup | Infra | Create Stripe + Paystack sandbox accounts | Register sandbox/test accounts for Stripe Express Connect and Paystack ahead of integration work. | DevOps / Cloud / Pricing Analyst | P0 — Blocker | 1 | None | Both sandbox accounts active; API test keys stored securely. | Not started
FT-005 | PI 0 — Foundation & Setup | Architecture | Design core data model | Design schema for users, orgs, campaigns, donations, and disbursement records — disbursement modeled as a first-class entity from day one. | Architect / Lead Engineer | P0 — Blocker | 5 | None | Schema/ERD reviewed and approved; disbursement entity explicitly represented, not bolted on. | Not started
FT-006 | PI 1 — Core Build I | Payments | Integrate Stripe Express Connect | Implement donor-side checkout and org payout account creation using Stripe Connect (Express). | DevOps / Cloud / Pricing Analyst | P0 — Blocker | 8 | Stripe sandbox account (PI 0) | Test donation completes end-to-end in sandbox; org can complete Express onboarding. | Not started
FT-007 | PI 1 — Core Build I | Payments | Integrate Paystack payout | Wire org payouts for Nigeria/Kenya/Ghana through Paystack's separate API/dashboard. | DevOps / Cloud / Pricing Analyst | P0 — Blocker | 8 | Paystack sandbox account (PI 0) | Test payout to a sandbox org account succeeds for all 3 target countries. | Not started
FT-008 | PI 1 — Core Build I | Payments | PCI-safe checkout implementation | Use Stripe/Paystack hosted Checkout/Elements only — no custom card forms — to keep PCI scope at SAQ A. | DevOps / Cloud / Pricing Analyst | P1 — High | 3 | Stripe/Paystack integration | No raw card data touches platform servers at any point; confirmed via code review. | Not started
FT-009 | PI 1 — Core Build I | Architecture | Implement auth + org verification workflow | Build sign-up/login and an org verification step (what proof an org submits to be allowed to create a campaign). | Architect / Lead Engineer | P0 — Blocker | 5 | Data model (PI 0) | User can register; org can submit verification info; unverified orgs cannot publish a campaign. | Not started
FT-010 | PI 1 — Core Build I | Architecture | Build campaign CRUD + donor-facing page | Org can create/edit a campaign; donor-facing campaign page displays goal, progress, and story. | Architect / Lead Engineer | P0 — Blocker | 8 | Data model (PI 0) | Org can publish a campaign; public page renders and accepts a test donation. | Not started
FT-011 | PI 1 — Core Build I | Growth | Begin org outreach — verify & contact pilot cohort | Manually verify GoFundMe absence for remaining unchecked orgs (ACE Charity, Kuhenza, GFD) and begin outreach to the 10-org shortlist. | You (Business & Growth) | P0 — Blocker | 5 | Org Outreach Tracker | All 10 orgs have a verified GoFundMe status and a logged contact attempt. | Not started
FT-012 | PI 1 — Core Build I | Growth | Draft trust & transparency FAQ content | Write donor-facing copy explaining how fund tracking works, for use on the site during onboarding. | You (Business & Growth) | P2 — Medium | 3 | None | FAQ/explainer copy drafted and reviewed by team. | Not started
FT-013 | PI 1 — Core Build I | Growth | Define org onboarding verification criteria | Document what qualifies an org to be allowed onto the platform (registration proof, references, etc.). | You (Business & Growth) | P1 — High | 3 | None | Written verification checklist used by Architect to build the org-verification workflow. | Not started
FT-014 | PI 1 — Core Build I | Infra | Set up payment monitoring & alerting | Add monitoring/alerts for failed payments and payout errors so issues are caught immediately. | DevOps / Cloud / Pricing Analyst | P1 — High | 3 | Stripe/Paystack integration | A simulated failed payment triggers an alert to the team. | Not started
FT-015 | PI 2 — Core Build II | Architecture | Build receipt / milestone upload flow | Org can upload receipts/reports tagged to a campaign, creating the core spend-transparency audit trail. | Architect / Lead Engineer | P0 — Blocker | 8 | Campaign CRUD (PI 1) | Org uploads a receipt against a campaign; it's stored and associated with a specific expense/milestone. | Not started
FT-016 | PI 2 — Core Build II | Architecture | Build donor statement generation | Generate a structured summary for donors showing where their donation went, not just a raw photo feed. | Architect / Lead Engineer | P1 — High | 5 | Receipt upload flow | Donor can view a statement summarizing spend tied to their donation. | Not started
FT-017 | PI 2 — Core Build II | Architecture | Build org admin / back-office dashboard v1 | Give orgs a simple dashboard to manage campaigns, view donations, and upload receipts in one place. | Architect / Lead Engineer | P1 — High | 8 | Campaign CRUD, receipt upload flow | Org can log in and manage all active campaigns and receipts from one dashboard. | Not started
FT-018 | PI 2 — Core Build II | Payments | Implement fee-model math in checkout | Translate the fee calculator logic (platform fee + processor fee + optional tip) into live checkout calculations. | DevOps / Cloud / Pricing Analyst | P0 — Blocker | 5 | Fee/tip structure decision (PI 0) | Checkout correctly itemizes and deducts platform fee, processor fee, and optional tip on a test donation. | Not started
FT-019 | PI 2 — Core Build II | Payments | Research LemFi partner API availability | Contact LemFi business development directly to confirm whether a partner/business API exists for the diaspora remittance corridor. | DevOps / Cloud / Pricing Analyst | P3 — Low | 2 | None | Written answer from LemFi (yes/no on partner API) logged in the tracker; decision made on whether to pursue further. | Not started
FT-020 | PI 2 — Core Build II | Growth | Finalize pilot org cohort commitments | Convert outreach contacts into committed pilot organizations ready to launch a campaign. | You (Business & Growth) | P0 — Blocker | 5 | Org outreach (PI 1) | At least 5 orgs have confirmed they will launch a campaign at soft launch. | Not started
FT-021 | PI 2 — Core Build II | Growth | Publish fee & pricing page | Write and publish the public-facing page explaining the platform's fee structure transparently. | You (Business & Growth) | P2 — Medium | 2 | Fee/tip structure decision (PI 0) | Pricing page live on site, matches actual checkout math. | Not started
FT-022 | PI 3 — Compliance & Hardening | Compliance | Engage payments/fintech legal counsel | Get legal confirmation on whether the milestone-based disbursement flow (holding funds pending receipt verification) stays under Stripe's Connect umbrella or triggers a separate money-transmitter obligation. | You (Business & Growth) | P0 — Blocker | 3 | None | Written legal opinion received before the milestone-holding mechanic is built or enabled with real money. | Not started
FT-023 | PI 3 — Compliance & Hardening | Architecture | Implement milestone-holding disbursement mechanic | Build the mechanism to hold donor funds until a receipt/milestone is verified, then release to the org. | Architect / Lead Engineer | P0 — Blocker | 8 | Legal sign-off (this PI) | Funds visibly held against a milestone in sandbox and released only after a receipt is marked verified. NOT enabled in production before legal sign-off. | Not started
FT-024 | PI 3 — Compliance & Hardening | Architecture | Build public audit-trail view (v1) | Public-facing view per campaign showing verified spend history, for donor trust. | Architect / Lead Engineer | P2 — Medium | 5 | Receipt upload flow (PI 2) | Any visitor can view a campaign's spend history without logging in. | Not started
FT-025 | PI 3 — Compliance & Hardening | Payments | End-to-end payment testing across all 3 countries | Run full test transactions donor (UK) -> platform -> org payout for Nigeria, Kenya, and Ghana. | DevOps / Cloud / Pricing Analyst | P0 — Blocker | 5 | Stripe + Paystack integration (PI 1) | A real (small-value) test transaction completes successfully end-to-end for each of the 3 countries. | Not started
FT-026 | PI 3 — Compliance & Hardening | Infra | Security & monitoring hardening | Review auth, data access, and payment monitoring ahead of handling real donor funds. | DevOps / Cloud / Pricing Analyst | P1 — High | 5 | Monitoring setup (PI 1) | Security review checklist completed with no open critical items. | Not started
FT-027 | PI 3 — Compliance & Hardening | Growth | Prepare org onboarding materials | Create simple onboarding guide/walkthrough for pilot orgs to use the platform at launch. | You (Business & Growth) | P2 — Medium | 3 | Admin dashboard (PI 2) | Onboarding guide ready to send to committed pilot orgs. | Not started
FT-028 | PI 4 — Soft Launch / MVP | Launch | Launch first pilot org cohort | Go live with committed pilot organizations' campaigns to real donors. | All (joint) | P0 — Blocker | 5 | All prior PIs | At least 5 org campaigns are live and able to accept real donations. | Not started
FT-029 | PI 4 — Soft Launch / MVP | Launch | Production cutover & live monitoring | Move from sandbox to production Stripe/Paystack accounts; confirm monitoring/alerts are active in production. | DevOps / Cloud / Pricing Analyst | P0 — Blocker | 3 | End-to-end testing (PI 3) | Production accounts live; a test alert successfully fires in production monitoring. | Not started
FT-030 | PI 4 — Soft Launch / MVP | Growth | Monitor donor acquisition & early retention | Track first-week donor numbers, repeat-donor rate, and campaign engagement post-launch. | You (Business & Growth) | P1 — High | 3 | Launch | Baseline metrics dashboard reviewed weekly for first month post-launch. | Not started
FT-031 | PI 4 — Soft Launch / MVP | Architecture | Bug triage & hotfix process | Set up a lightweight process for logging and fixing launch-week issues quickly. | Architect / Lead Engineer | P1 — High | 2 | Launch | Triage process documented; first-week issues logged and resolved or scheduled. | Not started

## PI Roadmap Summary
Fund&Trace — PI Roadmap Summary
High-level view of each Program Increment on the way to MVP. Full detail lives in the Ticket Backlog tab.
PI / Iteration | Goal | Key deliverables | Gating dependency
PI 0 — Foundation & Setup | Align on scope; stand up base infra and design the data model. | Geography + fee decisions, repo/CI/CD, Stripe & Paystack sandboxes, core data model design | None — this unblocks everything else
PI 1 — Core Build I | Get payments, auth, and campaign pages working end-to-end in sandbox. | Stripe + Paystack integration, PCI-safe checkout, auth/org verification, campaign CRUD, outreach to pilot orgs begins | PI 0 complete
PI 2 — Core Build II | Build the actual differentiator: receipts, statements, and org back-office. | Receipt/milestone upload, donor statements, org admin dashboard v1, live fee math in checkout, pilot cohort commitments finalized | PI 1 complete
PI 3 — Compliance & Hardening | De-risk the milestone-disbursement flow and prove payments work for real. | Legal sign-off on fund-holding flow, milestone-disbursement mechanic, public audit-trail v1, full 3-country payment testing, security hardening | Legal sign-off is a hard blocker before enabling fund-holding in production
PI 4 — Soft Launch / MVP | Go live with the first pilot org cohort and start learning from real usage. | Production cutover, first campaigns live, donor acquisition monitoring, bug triage process | PI 3 complete, especially legal sign-off